## SumamryReport
Total SRs Performed
S.No. | SR Category | Number
1 | LIVE Deployed SRs | 0
2 | TEST System Deployed | 3
3 | In-Progress | 6
4 | CouldNotReproduce | 0
| Total SR Number | 9

## LIVE_DEPLOYED
S.N | SR Number | Description | Created date | Priority | Status | Type | Remarks | Deployment

## TestSystem_Deployed
S.N | SR Number | Description | Created date | Priority | Status | Type | Remarks | Status
1 | EMM6-0055 | Customs Quarter Report | 30/09/2015 | Urgent | Resolved | Change Request | The Report has been generated and supplied to Euro-Mit. Also, the daily-custom-fix has been maintained in Test Server which needs to be verified by Euro-Mit. | Deployed in the Test Server
2 | EMM6-0065 | Create a report from the system with all NEU coils in Stock | 27/08/2015 | High | Resolved | Task | The Report has been generated and sent to Euro-Mit for verification. Will be verified Next week. | Resolved and Sent Report
3 | EMM6-0044 | CCC Task Management Corrections | 2015-11-09 | High | Resolved | Feature Request | While Writing the data from the "PIO" program, no data loaded to the table. Problem with CRC of database schema. | Deployed in test system

## In-Progress
S.N | SR Number | Description | Created date | Priority | Status | Type | Remarks | Deployment
1 | EMM6-0066 | Number of digits for "ADD.costs"box to small | 28/08/2015 | Medium | In Progress | Cosmetic | The Cosmetic changes as well as some changes in the report logic has been made. To accommodate 9 digits in Add. Costs in the invoices modules of the EMS system. Waiting for Verification from Euro-Mit | Partially Deployed in Test System.
2 | EMM6-0064 | Check reports based on palletized or on produced materials for truck PW and ETD date | 26/10/15 | Medium | In Progress | Task | Sr Has some question, Answered all the inquiry. | Partially deployed in test system
3 | EMM6-0022 | Laser Api freature expansion | 2015-11-05 | High | In Progress | Task | Fetch maximum value for all measurement. | In local
4 | EMM6-0061 | When coil number is ending with xj0 or higher it disappears | 2015-12-10 | Medium | In progress | Bug | There is no such type of problem while testing in local as well as test system. | In local
5 | EMM6-0067 | Check if the value of CL/W1750+ and IndB8+ gets changed when Value of Grade has been changed. | 30/10/15 | Medium | In Progress | Task | Till now, we cannot found any evidance from which cl and b8 is changed automatically. | In local
6 | EMM6-0063 | Revise the coilnumbersystem | 16/10/15 | Medium | In Progress | Change request | Maintaining the sequences of the coil number. | In local

## CouldNotReproduce
S.N | SR Number | Description | Created date | Priority | Status | Type | Remarks | Deployment