## 20150904
Euro-Mit STAAL Weekly Defect Report
S.No. | Created Date | ID | Email Subject | Issue/Description | Issue Type | Status | Remarks | Priority | No. of Occ. | Planned Release Date | Actual Release Date
1 | 2015-07-09 | EMM6-0009 |  | Split R780 into PL and CIF | Bug | Resolved | Removed CIF from the PL was placed in separate report program. | Medium
2 | 2015-07-09 | EMM6-0011 |  | Change output APPLY CUSTOMS | Task | In Progress | Some Dutch characters must be translated into English (Hand Written) | High
3 | 2015-06-11 | EMM6-0022 |  | Laser Topic :- Make the API functionality working with progress | Project | Resolved | Toolbar buttons for 2 laser devices were modified and implemented. | High
4 | 2015-07-10 | EMM6-0015 |  | Print monthly reports ( Making Reports Automation ) : | Feature Request | Resolved | All the reports (txt as well as pdf format) completed and deployed to test system. Javra will prepare detail document on Monthly Reports automation and send to Euro-Mit. | Low
5 | 2015-07-09 | EMM6-0008 |  | Enhance R503 and R504 | Task | Resolved | Euro-Mit needs to provide document regarding the SRs. | Low
6 | 2015-08-20 | EMM6-0025 |  | Import duties not on sales report | Bug | Resolved | Please see the attached document and confirm about the issue. | Medium
7 | 2015-08-21 | EMM6-0026 |  | Force system to check IMA box in “trucks” | Task | Resolved | Deployed to test system. | Medium
8 | 2015-08-21 | EMM6-0027 |  | Automatically calculating import duties | Bug | Resolved | Local environment | Medium
9 | 2015-08-21 | EMM6-0028 |  | Not printing a line automatically on a invoice | Bug | Resolved | Local environment | Medium
10 | 2015-08-27 | EMM6-0031 |  | USD in cashflow | change request | In Progress | Local environment | Medium
11 | 2015-08-27 | EMM6-0032 |  | Due date in iinvr749 | Bug | Resolved | Local environment | Medium
12 | 2015-08-27 | EMM6-0033 |  | Copy order 1-1 | change request | Resolved | Local environment | Medium
13 | 2015-08-27 | EMM6-0034 |  | Price in sizes | change request | Resolved | Local environment | Medium
14 | 2015-08-27 | EMM6-0035 |  | Split up EU and NEU material in availability | change request | Resolved | Local environment | Medium

## 20150911
Euro-Mit STAAL Weekly Defect Report
S.No. | Created Date | ID | Email Subject | Issue/Description | Issue Type | Status | Remarks | Priority | No. of Occ. | Planned Release Date | Actual Release Date
1 | 2015-07-09 | EMM6-0008 |  | Enhance R503 and R504 | Task | In Progress | Euro-Mit needs to provide document regarding the SRs. | Low
2 | 2015-07-09 | EMM6-0011 |  | Change output APPLY CUSTOMS | Task | In Progress | Some Dutch characters must be translated into English (Hand Written) | High
3 | 2015-07-10 | EMM6-0015 |  | Print monthly reports ( Making Reports Automation ) : | Feature Request | Resolved | All the reports (txt as well as pdf format) completed and deployed to test system. Javra will prepare detail document on Monthly Reports automation and send to Euro-Mit. | High
4 | 2015-08-21 | EMM6-0028 |  | Not printing a line automatically on a invoice | Bug | Resolved | Deployed to the Test system | Medium
5 | 2015-08-27 | EMM6-0031 |  | USD in cashflow | change request | Resolved | Deployed to the Test system | Medium
6 | 2015-09-09 | EMM6-0038 |  | Calculate import duties for NEU | Task | Resolved | Deployed to the Test system | Medium
7 | 2015-09-09 | EMM6-0040 |  | Dollar Bankaccount on invoice | change request | Resolved | Deployed to the Test system | Medium
8 | 2015-09-11 | EMM6-0042 |  | Place '?' in Sizes Tab if the order price value is '?' while creating order. | Bug | Resolved | Deployed to the Test system | Medium
9 | 2015-09-07 | EMM6-0007 |  | Improve R569 | Task | Resolved | Ready for Live deployment | Medium
10 | 27/8/2015 | EMM6-0032 |  | Due data in iinvr749 | Bug | Resolved | Deployed to the Test System | Medium
11 | 27/8/2015 | EMM6-0033 |  | Copy order 1-1 | Change Request | Resolved | Deployed to the Test System | Medium
12 | 27/9/2015 | EMM6-0035 |  | Split up EU and NEU material in availability | Change Request | Resolved | Deployed to the Test System | Medium
13 | 2015-08-09 | EMM6-0037 |  | Label Missing and Control Not Aligned to Text | Change Request | Resolved | Ready to deployed in Test System | Low
14 | 2015-10-09 | EMM6-0039 |  | INF-1 Report | Change Request | Resolved | Ready for Live deployment | Medium
15 | 2015-10-08 | EMM6-0009 |  | Split R780 inti PL and CIF | Bug | Resolved | Deployed to the Test System | Medium
16 | 21/8/2015 | EMM6-00025 |  | Import Duties not on Sales Report | Bug | Resolved | Deployed to the Test System | Medium
17 | 26/6/2015 | EMM6-0022 |  | Make the API functionality working with progress | Task | In Progress | Added New toolbar button for the Begin of metting and End of metting and Deployed to the Test System. | High
18