## SR Summary@24-02-2016
SR Summary Report
SR ID | Cust. Ref | Title | Type | Priority | Severity | Module | Version | Status | Resolution | Assignee | Creator | Description | Start(Plan) | Test(Plan) | Due(Plan) | Started | Resolved | Verified | Closed | Est.Hrs | Real.Hrs | Rem.Hrs | Comments | Change List
EMM6-0083 |  | Laser Data Testing with Euro-Mit | Task | High | Major | Application support | V1.0 REL 01 | 2000 - Open |  | hari |  | Testing Laser Data Integration | [7 empty] | 0 | 0 | 0
EMM6-I-0030 |  | Knowledge Sharing Session | Task | Med | Moderate | Project Management | V1.0 REL 01 | 2000 - Open |  | hari |  | Training and Knowledge Sharing Session in the Project | [7 empty] | 0 | 0 | 0
EMM6-0036 |  | Check Performance of the System to find performance related issues. | Task | Med | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | 1. Check and find out slow performance issues in the system during CRUD operations. 2. Check and create indexed that are required in order to achieve fast performance. 3. Modify other programs if necessary. |  |  |  | 01/10/2015 |  |  |  | 0 | 0 | 0
EMM6-0044 | 1249 | CCC Task Management corrections | Change Request | High | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | Attached document contains a screen shot of EMM task management cutting. This field has to be filled in by operator Data is connected Data to be checked by EMM 1. Task No. belongs to an order. Operator fills in “Task No”. à “Order No” will be filled by EMM system. 2. Change “Date” into “Date begin” 3. Change “Operator” into “Date End” 4. “Time end” à Always after “Date begin” & “Time begin” 5. Change “External machine” into “Operator” 6. A) Operator fills in “Step”. EMM system checks à Width of “Step” and Width of “Task No” are identical. B) à”Batch”, ”Shape 1,2” will be filled by EMM system. 7. Operator fills in “Plates 1,2” & “Height 1,2”. EMM system checks Height à Plates and Plates à Shape. 8. Change Remainder, Remain wgt, Re-use and Reject in another sequence according attachment. Add Line “Remove”. Remove means: Remove coil from machine, coil will be used later in the same order. 9. 4 possibilities: Pos 1: Remainder “Yes” , Re-use “No” , Remove “Yes”. Remain Wgt will be filled by operator. Pos 2: Remainder “Yes” , Re-use “Yes”, Remove “No”. Remain Wgt will be filled by EMM system. (Theoretical weight). Pos 3: Remainder “Yes” , Re-use “Yes”, Remove “Yes”. Remain Wgt will be filled by operator. Pos 4: Remainder “No”, Re-use “No”, Remove “No”. No Remain Wgt. 10. “Remain Len” à will be filled by EMM system. 11. If Remove “Yes” à Print C-Label. (question). 12. If Reject “Yes” à Add remark! Mister deMarco is also contact person from EMS, that will be included when contact is made with Johan |  |  |  | 14/09/2015 |  |  |  | 0 | 0 | 0
EMM6-0055 | 1260 | Customs quarter report | Change Request | Urg | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | Custom quarter report has to be send to customs before October 30. Report is half made by Eric but not finished. this is urgent request because EMS will get big penalty if report is not complete. Check the attachments. |  |  |  | 01/10/2015 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0072 |  | Create a monthly report with SRM2FG and FG2SRM Updates | Task | Med | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | neha |  | In the monthly report we have two columns: SRM2FG and FG2SRM SRM2FG : SRM (1st grade & rerun) -> 2(by means of mutate & machines) ->FG FG2SRM : FG -> 2(by means of mutate) --> SRM (1st grade & rerun) I would like to have a separate report which shows: SRM2FG : SRM (1st grade) --> 2(by means of mutate) --> FG FG2SRM : FG --> 2(by means of mutate) --> SRM (rerun) Based on quantity, amount and time frame |  |  |  | 29/12/2015 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0074 |  | Enhance Laser Device Data Integration | Task | High | Major | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | We need relevant data feed in EMM5 system from the data during measuring period from START to END. The data will contain huge numbers from which we need to calculate relevant (max) data. During the process csv or txt file need to be created with filename(date_timestamp) for uniqueness and data verification. |  |  |  | 19/11/2015 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0077 |  | Wrong Cutting Number in Monthly Report | Bug | Med | Major | Application support | V1.0 REL 01 | 5000 - In Progress |  | neha |  | The cutting number in monthly report are not right. Attached files for refrence. |  |  |  | 25/11/2015 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0091 |  | Database Connection in EMM4 and convert to latest version | Task | Med | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | Provide the steps how to connect EMM4 database. Also do some research to convert EMM4 database into latest version. |  |  |  | 11/01/2016 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0096 | Ticket_1270 | Problem with tab trucks in slit order | Bug | NP | Undefined | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | Hari, Sometimes when you confirm an order using "enter" green icon you'll be in the next order. My thoughts about this is maybe thru a memory leak. Because you can't reproduce this error. But I know values will be entered in the memory and later reread again. So maybe it's possible that a user (laptop and desktops here) have DDR3 ram, non ecc. So it's possible a leak can occour. Can this be solved? I really don't think so or you can set a security messeare for this using a txt file where temp data is stored, but it takes to much time. Well think about this possibility, I really don't think it's solveable but maybe you know of other occourences where this happens. Attached mail with screenshot of order where it happend |  |  |  | 10/02/2016 | 02/11/2015 |  |  | 0 | 0 | 0
EMM6-0101 |  | Automation on the Shipments | Feature Request | Med | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | amit |  | Attached the print screen for the request to automatically upload new coil data in our system. When we input new shipments we have to input each coil manually. We would like to make this easier. I attached 2 files. PDF is showing instructions where we want the data to be inputted and Excel is the actual data we need to upload in EMM. Step-by-step: 1. First page PDF: EMS staff will make new shipment (No help from Javra needed) 2. Second page PDF: EMS staff will make new Bill of Lading in this new shipment. (No help from Javra needed) 3. Third page PDF: Inputting of the master coil data, here we want Javra to help and make an “Import button” so all coils can be loaded at once instead of typing them 1 by 1 which is very mistake sensitive. The excel file contains columns A till K. Each column has different value which needs to be loaded into our system. So column A should be loaded in the field “Ext.col-nr+” and column B should be loaded in the field “Insp.nr+” etc. etc. Each row in the excel file represent 1 master coil. If EMS saves the excel file somewhere in a folder under the name of the matching Bill of Lading number, would it be possible to upload all coil data into the system at once?? Also make sure that the other fields (not indicated by a letter) will keep their original link in our system to avoid problems. |  |  |  | 16/02/2016 | 18/02/2016 |  |  | 0 | 0 | 0
EMM6-I-0015 |  | Deploying Euro-Mit Test System from Local Environment | Task | Med | Moderate | Application support | V1.0 REL 01 | 5000 - In Progress |  | Not Assigned |  | All the updated programs and required files will be deployed to Euro-Mit test system to check EMM5 Test System at Euro-Mit Server. |  |  |  | 23/09/2015 | 18/02/2016 |  |  | 0 | 0 | 0
EMM6-I-0032 |  | Test every report for performance improvement | Task | Med | Major | Application support | V1.0 REL 01 | 5000 - In Progress |  | neha |  | Please test each and every report if it is taking a long time period. If yes, look into the database why it is taking long time period. Find the solution for performance improvement in the report generation. |  |  |  | 24/02/2016 | 18/02/2016 |  |  | 0 | 0 | 0
EMM6-0004 | find solution for daily-customs-fix | find solution for daily-customs-fix | Task | High | Major | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | hari |  | m) run fix on existing data for R502 !!! In many stages production process data is collected that is to be reported to customs periodically. Various fields are set in various stages tru triggers or procedures, in these several mistakes or unifinshed. h) fix problem incorrect values coz of mistakes or lacking code in triggers (h and m are the same problem) |  |  |  | 15/07/2015 | 12/08/2015 |  |  | 0 | 0 | 0
EMM6-0008 | enhance R503 and R504 | enhance R503 and R504 | Task | Low | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | neha |  | f) enhance R503 and R504 to meet user-requirements R503 = CALL OFF R504 = UNLOADING MSG These reports are new, functional but can be improved to ease users. |  |  |  | 15/10/2015 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0013 | change biz-logics regarding customs doc | change biz-logics regarding customs doc | Task | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | hari |  | a) adjust biz-rules so only 1 document can be selected, however! a truck-load may contain used material from both EU and NEU and thus theoretically two customs-docx are required. Please examine behavior of check-boxes in truck mgt. EUA,EUX,T1,IMA. (or none at all) When setting EUA this will reset EXA, all scenarios should be like this, there can be only ONE. (An alternate solution would be RADIO-BTN ! And perhaps also change dataschema, combining several logic fields into a char field. For now this surely is too big.) The second part is some validation. At this moment responsibility is with user. The user will indicate what document is applicable, before goods are produced. A truckload can have different goods, ONLY EU, ONLY NEU, BOTH EU AND NEU. (EU = European goods, NEU = non-European goods) Depending on what goods are used EU/NEU certain document type is applicable yes or no. If EU material then doctype must be EUA/EXA and never T1/IMA. If NEU material used then T1/IMA and never EUA/EXA. ! This contradicts per truck only one doctype ! The expectation within Euromit is this is a temporary situation, no more EU material will arrive, thus the need for EUA/EXA will disappear. Still, even with "ONLY ONE DOCTYPE ALLOWED" there is workaround for combined loads. Workaround: begin with truck gets EUA/EXA, apply customs, confirm customs(this creates record tdoc), change truck gets T1/IMA and repeat apply+confirm customs record a second document. |  |  |  | 25/08/2015 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0023 |  | Move sequence logic to trigger | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | hari |  | In the existing order creation program, the cut and slit order cannot be created from their own program because of issue with the sequence used for the primary key field. This issue can be resolved by adding the logic in trigger while creating an order. Once this is done, delete the main order creation program. Also make sure, the user can create cut or slit order using cut/slit order program. |  |  |  | 28/07/2015 | 12/08/2015 |  |  | 0 | 0 | 0
EMM6-0032 |  | Due date in iinvr749 | Bug | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | hari |  | Due date is not changing when the days box is changed. |  |  |  | 02/09/2015 | 02/09/2015 |  |  | 0 | 0 | 0
EMM6-0075 |  | Upgrade EMM5 System into Progress 11.5 Version | Task | Med | Major | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | frank |  | Currently EMM5 system is running in Open-Edge Progress 10.1B version. The system should be upgrade to new version of progress to have some issue fixed with version 10.1B and to enhance performance of the system. |  |  |  | 25/01/2016 | 25/01/2016 |  |  | 0 | 0 | 0
EMM6-0078 |  | Modify CRM report in order to print 4 reports without using print/batch module | Task | Med | Minor | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | neha |  | Modify CRM report in order to print 4 reports without using print/batch module |  |  |  | 09/12/2015 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0085 |  | Update Module so that sys and mo5 user group can set Cutting task status to 300 | Task | Med | Moderate |  | V1.0 REL 01 | 6000 - Resolved | Completed | Not Assigned |  | Previously there was hard code due to which if the task is Cut "K" type in the code only 3 users are set in such a way that only they can change the status from 200 to 300. The users are : ecl egan566 mo5 Change module to exclude ecl and egan566 and make user group sys and mo5 to do the task. |  |  |  | 17/12/2015 | 23/12/2015 |  |  | 0 | 0 | 0
EMM6-0089 |  | Change the logic of import duties from 35.9 % to 0 according to the new Dutch rule. | Change Request | High | Major | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | amit |  | Request is to remove the calculation for import duties (35.9% x cif purchase price) when import duty paid ticket box is checked. The most simple solution is to change the 35.9 to 0. But better is to remove the calculation so the line with import duties is also not showed anymore. |  |  |  | 08/01/2016 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0098 |  | Change the field in companies to have 70 characters instead of 56 | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | neha |  | Change the field in companies to have 70 characters in stead of 56. This is used in delivery terms in gcomm but the field is missing data |  |  |  | 11/02/2016 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0100 |  | No address in Client/Transporter, gives empty fields in CMR | Bug | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | neha |  | No address in Client/Transporter, gives empty fields in CMR. |  |  |  | 16/02/2016 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0102 |  | overwriting grade not working anymore | Bug | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | neha |  | when stating text /grade in box next to dropdown lisst for “Grade” the standard text that belong to the selected grade should be removed from all docs as SaC, PL and invoice. This worked but is not working anymore. For more details please check attached documents. |  |  |  | 18/02/2016 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0103 |  | Misplace of Coil number,purchase value in the shipment. | Bug | Med | Moderate | Application support | V1.0 REL 01 | 6000 - Resolved | Completed | amit |  | First shipment I was going to start was 2838 (Edith Maersk) Strangely enough the #Coils & Quantity in the first screen was “0” If I go 1 shipment up (2837) we see there are coils and quantity, but if I go back to shipment 2838, it shows the same quantity and # coils as shipment 2837. If I go 1 shipment up (2839) we see there are coils and quantity, but if I go back to shipment 2838, it shows the same quantity and # coils as shipment 2839. So it starts with 0, but when I select other shipment and go back to 2838 the coils and quantity stays the same as the previous checked shipment??? Before I start with the price adjustment, I would like to know where this mistake is coming from and if it has no influence on the price adjustment? And one error message also arose in the system "find first/last no found ". |  |  |  | 22/02/2016 | 24/02/2016 |  |  | 0 | 0 | 0
EMM6-0099 | EMS ref no 1188 | Change purchvalue of mastercoil per coil | Change Request | Urg | Undefined | Application support | V1.0 REL 01 | 7000 - Verified | Completed | marcovl |  | In the module shipments are booked the mothercoils with a certain price. For the attached list of BL's EMS is receiving revised purchase invoices. It is too much work to change manual. request is to make a tool so price of each coil will be changed. Attached excel list with BL's who are should be changed and word file with description of the process. |  |  |  | 11/02/2016 | 16/02/2016 | 24/02/2016 |  | 0 | 0 | 0
EMM6-0002 | Customs AD608 | Customs AD608 | Support SR | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | ** unfinished topic customs, the topic is large and better to split into smaller topics a) adjust biz-rules so only 1 document can be selected, however! a truck-load may contain used material from both EU and NEU and thus theoretically two customs-docx are required b) cosmetic, re-arrange widgets in various modules where truck-record is shown c) alter the result of APPLY CUSTOMS, some info is missing for new situation d) implement validation on mrn-number e) re-organize the report R780 PACKINGLIST, the option CIF must be taken out and inserted elsewhere f) enhance R503 and R504 to meet user-requirements g) enhance R502 to meet customs-requirements (huge) * scrapping coil -- first scrapping SS * correct coil * adjust legenda h) fix problem incorrect values coz of mistakes or lacking code in triggers i) alter the R569 to meet requirements j) fix issue with certain text to appear on invoice in certain cases k) merge all invoices into a single interface (huge) l) verify validation is present when creating invoice // yes, present in live-env m) run fix on existing data for R502 !!! n) when R502 shows correct data change the format into excel AD608 is reference to EU-regulation issed dd 14.5.2015 |  |  |  | 09/07/2015 | 17/11/2015 | 24/02/2016 | 30/11/2015 | 0 | 0 | 0
EMM6-0003 | convert R502 into xlsx | convert R502 into xlsx | Feature Request | Low | Minor | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | n) when R502 shows correct data change the format into excel Currently the output of R502 (ZUIVERING) is comma-separated, the user responsible now have to manually convert from csv to xlsx. This SR is request to ease the operation for the user and avoid mistakes. |  |  |  | 28/07/2015 | 29/07/2015 | 24/02/2016 | 09/02/2016 | 0 | 0 | 0
EMM6-0006 | text about customs must appear on salesinvoice | text about customs must appear on salesinvoice | Task | High | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | j) fix issue with certain text to appear on invoice in certain cases Depending on material used and delivery terms certain text must appear. In the code there is a mistake. |  |  |  | 10/07/2015 | 14/07/2015 | 04/02/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0007 | improve R569 | improve R569 | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | i) alter the R569 to meet requirements R569 = INF-1, a document necessary in certain cases. Unfinished, currently merely a setup to gather the required information, the user is transferring this information into an excel-template and make final document from there. This is request is to complete gathering the required data, and beautify the result including header and such thus simplifying the process making final document. |  |  |  | 16/07/2015 | 10/08/2015 | 04/02/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0010 | validate mrn-nbr | validate mrn-nbr | Task | High | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | d) implement validation on mrn-number When CONFIRMING CUSTOMS a number is inputted, there must be a validation on this number. Customs has provided good documentation for this, see attached "Berekening_controlecijfer_MRN-GRN.pdf". However Euromit situ must be considered, it wont be straightforward. This issue started out to be very simple, customs demands the nbr inputted to system is validated, like must be 18 chars and more (see the pdf). However due to Euromit specific business the intended interface (from truck mgt CONFIRM CUSTOMS) to input the nbr will be bit more complicated. The number inputted will be for T1-document (this is an mrn-nbr), also for EXA/EUA-document (this is an mrn-nbr), also for agreement ART546 (this is not an mrn-nbr). The validation is only applicable to mrn-numbers. The users are instructed to input mrn-nbr without "MRN", so they will input 18 chars (*1*). Incase ART546 the users are instructed to input "ART546", so when leaving widget create if-then or case and only run the validation if input does not begins ART546. After commit a record tdoc is created, the nbr must be uniq, hence when user is inputting ART546 somewhen unig ref is added. (*1*) The 18 chars is applicable to the new regulations. As Euromit still has material under old regulations there may be situations the mrn-nbr wont be 18 chars! This is major headache, how to determine when to validate an mrn-nbr yes or no. |  |  |  | 10/07/2015 | 14/07/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0014 | hide widgets top-right-corner | hide widgets top-right-corner | Task | Low | Cosmetic | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | hide widgets {changedby,date,time,sendtodb,and such} from all modules. This is about auditing, avoiding questions from users who often don't understand many users can change a record. It also reduces the data shown, many screens are overcrowded. |  |  |  | 15/07/2015 | 16/07/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0018 |  | Create maintenance prograe to update temporary reference number to final reference number. | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Need some maintenance program using which users can update temporary reference numbers to final reference number. |  |  |  | 28/07/2015 | 29/07/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0019 |  | Modify business logic so that users can input temporaray reference number. | Task | Low | Minor | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When there is not generated final reference number , custom will provide temporary reference number. For a temp Number, the current instruction is to input “T” + “18digitnbr”. Implement this validation so that user can enter a temporary number in Custref Number. |  |  |  | 16/07/2015 | 16/07/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0021 |  | remove block containing changed-by and such from every module in top-right-corner | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Why : The information can be misleading, users often don’t understand a record could be changed by so many users. How : Create script to set flag hidden to true for those widgets, this wont effect EMM at all. Notes : -- already the feature “General Audit” is disabled for users to avoid abuse from users. -- widgets to hide: <table>tsendxusec , <>dsend , <>tsendtime, <>tsendtodb, <>xdepc -- hiding the widgets should be followed by a cosmetic change, re-arrange the remaining widgets -- how to test: run the script in test-env, then start every module, every tabfolder, no errors should be encountered, if succes choose date+time to run script live. |  |  |  | 06/07/2015 | 14/07/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0022 |  | Laser Topic :- Make the API functionality working with progress | Task | High | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | The API provided has the set of functionalities which needs to accessible from progress. Make sure they are accessible and working from progress. |  |  |  | 26/06/2015 | 20/11/2015 | 04/02/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0025 |  | Import duties not on sales report | Bug | Med | Undefined |  | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | No import duties from slit invoice is mentioned in sales report (IINVR770.P) column non-ope. Import duties from laminations invoice is mentioned on sales report. Example: Invoice 20150916 attached. Laminations invoice Invoice 20150898 attached. Slit coil invoice Report sales attached If there are import duties on the invoice this should be mentioned on the sales report (IINVR770.P) in the column non-ope. |  |  |  | 21/08/2015 | 04/09/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0026 |  | Force system to check IMA box in “trucks” | Change Request | Med | Undefined | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | This issue is custom related. When box duty paid and box NEU are checked then in 100% of the cases the IMA box in tab "Trucks" should be checked. |  |  |  | 24/08/2015 | 15/09/2015 | 08/09/2015 | 11/02/2016 | 0 | 0 | 0
EMM6-0027 |  | Automatically calculating import duties | Bug | Med | Undefined |  | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | If EMS has to make invoice with import duties we have to search in the system the amount and input manualy when making the invoice. The system calculate the duties in report R780. This amount should be mentioned automatically when making the invoice. In the attachment is showed the screens. |  |  |  | 24/08/2015 | 24/08/2015 | 08/09/2015 | 25/01/2016 | 0 | 0 | 0
EMM6-0028 |  | Not printing a line automatically on a invoice | Bug | Med | Undefined |  | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | In case we have EU box checked in slit order screen, there are no duties, but a line is automatically added. It should completely disappear when EU box is checked. |  |  |  | 24/08/2015 | 01/09/2015 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0034 |  | Price in sizes | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Automaticly fill price in size |  |  |  | 31/08/2015 | 04/09/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0038 |  | Calculate import duties for NEU | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Previously while calculating import duties (30.9%) , the logic was implemented for both EU and NEU. Update the logic only for NEU materials. |  |  |  | 10/09/2015 | 10/09/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0039 | Sales | INF-1 report | Change Request | Med | Minor | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Improve INF-1 add information as mentioned in the attachment |  |  |  | 10/09/2015 | 11/09/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0040 | Sales | Dollar bankaccount on invoice | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When invoice is in dollar print dollar account on the invoice. |  |  |  | 10/09/2015 | 11/09/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0043 | 1250 | B8 value block does not work | Bug | High | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Cannot Reproduce | Not Assigned |  | the demand of b8 value does not work in order 17941 |  |  |  | 15/09/2015 | 30/09/2015 | 03/11/2015 | 11/02/2016 | 0 | 0 | 0
EMM6-0048 |  | Can not set to Confirm staus once reset the value in some tasks | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Can not set to Confirm staus once reset the value in some tasks. task 277823 and 276772. |  |  |  | 15/09/2015 | 23/12/2015 | 03/11/2015 | 11/02/2016 | 0 | 0 | 0
EMM6-0049 |  | Analyze for the empty i/iinvr520 report when user generate same report two times | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When i/iinvr520 report is running, the invoices will be marked as exported (status change). But the department made a mistake and run it twice, thus giving a blank result. |  |  |  | 18/09/2015 | 28/10/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0050 | 1255 | Change paperwork date in slit date | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Request to change paperwork date in slit date for some reports |  |  |  | 18/09/2015 | 21/09/2015 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0056 |  | Create necessary icons for laser device data integration | Feature Request | Med | Minor | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | We need 4 icons for 1 laser device in EMM5 application which will make data integration at different levels. |  |  |  | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0057 | EMM6-0057 | when we insert our password in Emm5 live | Bug | Med | Moderate |  | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | when we insert our password in Emm5 live, after 2 times ok we can enter emm5 but it’s strange, its throw pop error message. Where did it come from? |  |  |  | 08/10/2015 | 07/12/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0058 | 1261 | EMM Problem Import Duties | Bug | Urg | Critical | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Please note: Import DUTIES at SALES invoices are not added in total amounts in overviews and other screens. Eg: SALES INVOICE 20150624 Finance/Sales invoices/ In above screen it shows “invoice amount” 38,696.22 Please note the total amount of this invoice is 38,696.22+11,478.31 = 50,174.53 FINANCE/FINANCE REPORTS/outstanding invoices/ debtor overview ( but also for overdueor all by invo or summary debtors) The amount in the overview is also without import duties which is wrong. The total invoice amount = 50,174.53! Please adjust asap as now we send wrong overviews to our customers!! |  |  |  | 08/10/2015 | 08/10/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0059 | 1258 | request small change layout invoice text | Change Request | Low | Cosmetic | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Please bring up the invoice text with about 2 or 3 lines. In below picture you can see between page-header and “INVOICE” there is quite some room, while at the bottom the line “Managing director “is almost in the page-footer. So please move up the printed text about 2 or 3 lines. |  |  |  | 08/10/2015 | 05/01/2016 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0060 |  | Find Out Coil List and Status in which Bert has changed GradeName and in production till Date | Support SR | Urg | Critical | Application support | V1.0 REL 01 | 8000 - Closed |  | Not Assigned |  | Somewhere in July I (Bert -> username is BVE) changed the grade name from many coils: · 20ZDKH75L -> 20ZDKH75 · 23ZDKH85L -> 23ZDKH85 · 27ZDKH95L -> 27ZDKH95 In below printscreen you can see where I changed the grade name. (Shipments->Mastercoils) Unfortunately for some strange reason also the CL/W1750 and the IndB8 has been changed (we do not know how? But system indicated that I changed it together with the grade name?) I am 100% sure I only changed grade name! (So next topic is to see why system automatically changed CL and IndB8 but this is for next week) Anyhow, we already traced back and changed CL and IndB8 back to original values for the available (not produced yet) coils at this moment. Now we also want to know which coils where used in production already in the period starting from when I changed the grade names (July) up to today. We are afraid that CL and IndB8 were also changed from these coils and that we informed wrong values to our customer. Therefore we want to know which coils (original 20ZDKH75L / 23ZDKH85L / 27ZDKH95L) which I changed to grade with no L, has been used in the past period after I changed grade name. As there are also lots of coils used where we did not changed the grade name, we have to find a way to see which coils (from July to today) where produced of which also the name was changed in July. Actually we need to know the following: Which coils were changed in Grade / CL or IndB8 from July till today (and if possible, which of these coils are used already and which coils are still available) I hope this makes things clear for you, if not feel free to call me tomorrow. I will be available for you. |  |  |  | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0061 |  | when coil number is ending with xj0 or higher it disappears | Bug | Med | Critical | Application support | V1.0 REL 01 | 8000 - Closed | Not a bug | Not Assigned |  | When a coilnumber is ending with xj0 or higher it disappears in task management operator. The operator from the cuttingline had this problem before, but don't know how it got fixed. |  |  |  | 14/10/2015 | 09/11/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0062 | 1235 | Invoice Laminations shows no ADD duty on invoice | Bug | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | In incoive laminations the ADD duty won't be shown on the invoice. See screenshot for the data inserted and see pdf screenshot for the result |  |  |  | 18/11/2015 | 18/11/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0063 | 1263 | revise the coilnumbersystem | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | We need to revise the method used to number the coils. Currently the coils are numbered after X in the following sequence: 01,02,03,04..09, 10,11...99, a0,a1,a2,a3,a4..a9,b0,b1..b9,c0,c1,c2..z9 But this will only let us have 360 combinations. I suggest to have to following method 01,02...09, 0a,0b,0c..0z,10,11..19,1a,1b..1z,20,21..9z,a0,a1..zz Thus giving us 1296 combinations. It is not needed to convert the old numbers this will be used for new coils, after the implementation. Why? We are going to have an order which wil result in 700+ numbers, and also a new one will come which is also large, so we are way beyond are current limit. |  |  |  | 30/10/2015 | 25/01/2016 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0064 |  | Check reports based on palletized or on produced materials for truck PW date and ETD date | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | As attachement you’ll find a document containing a question about what is calculated. As extra question if the “report on truck pw date”is indeed based upon palletized materials, is it possible to add an extra checkbox with “to produce on PW date”? |  |  |  | 28/10/2015 | 06/11/2015 | 25/01/2016 | 11/02/2016 | 0 | 0 | 0
EMM6-0065 |  | Create a report from the system with all NEU coils in Stock | Task | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | There are coils in the system which are EU or NEU (European material or Non European material). Create a report from the system with all NEU coils which are in stock. The report should contain the same information as what is on the customs report. |  |  |  | 28/10/2015 | 04/11/2015 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0066 |  | Number of digits for "ADD.costs"box to small | Feature Request | Med | Cosmetic | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Amount to be mentioned in add.costs is 133.860 USD But only 13386 is possible, this is not correct, please make the box bigger so also numbers up to 9 digits van be mentioned. Many thanks! |  |  |  | 30/10/2015 | 18/11/2015 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0067 |  | Check if the value of CL/W1750+ and IndB8+ gets changed when Value of Grade has been changed. | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | There were some coils whose CL/W1750+ and IndB8+ values have been changed automatically when the value of GradeName for those coils had updated. Analyze if this process is automatic or if there is some other reason which made this happen. |  |  |  | 30/10/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0068 |  | Change Error message block into Warning Block | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When an EU Order was made from NEU material, there appears an Error message block and the order can not be made. Change the Error block into Warning Block so that order can be made. |  |  |  | 04/11/2015 | 04/11/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0069 |  | Performance Issue in Capacity Checker Generating Report | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When generating report in LIVE, it takes quite long time and seems system hang. Find out the the performance issue in generating report if there is any. |  |  |  | 06/11/2015 | 06/11/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0070 |  | Analyze if the module is available to convert NEU coils into EU Coils | Task | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Check in EMM5 system if there is some module which will convert NEU coils into EU and vice- versa. |  |  |  | 17/11/2015 | 17/11/2015 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0071 |  | Develop a program module to convert NEU into EU and vice-versa | Task | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | There are no module to convert NEU coils into EU and vice-versa at the moment. Develop the module which will convert NEU coils into EU coils and vice-versa by authorized users. |  |  |  | 17/11/2015 | 10/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0073 |  | Fix issue in Pallet Management for number out of Range | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | There occurred error when coil number in coil system gets higher than 450. |  |  |  | 10/11/2015 | 18/11/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0076 |  | Create a script which will list NEU FG coils | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | There are still some FG NEU coils in the system. These coils migh need to convert into EU. Create an script to list all those FG NEU Coils. |  |  |  | 25/11/2015 | 26/11/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0079 |  | Modify FileNo Field in order to accept 15 AlphaNumeric Value | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Currently FileNo field can accept up to 10 numeric digit only. Modify the field to accept 15 alphanumeric value in it. |  |  |  | 08/12/2015 | 08/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0080 |  | Create Script to Delete some Trucks sent by Client | Task | Med | Minor | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Create Script to Delete some Trucks sent by Client |  |  |  | 09/12/2015 | 09/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0081 |  | Add Ref No. as per new coil numbering system with Slit Number | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Add new field in Task Management so as to display last three alpha numeric characters of the coil number with slit number. |  |  |  | 08/12/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0082 |  | Change the Warning Messages according to New Numbering System | Change Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | As the coil numbering system has been changed to new sequence, the warning messages related to the tasks should also be updated. Change the Warning Messages according to New Numbering System |  |  |  | 11/12/2015 | 20/01/2016 | 25/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0084 |  | Mutate a coil in Coil mgt – RM (o/ocoimrm.p) just like in Coil mgt – SRM. | Feature Request | High | Major | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Please give us the posibility to mutate a coil in Coil mgt – RM (o/ocoimrm.p) just like in Coil mgt – SRM In SRM it goes like this: Planning & Production => Coil mgt SRM => Mutate buton => ordernummer => oke. |  |  |  | 17/12/2015 | 17/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0086 |  | Create a module to set a truck ex ems | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | need to set a truck ex ems but it can’t be done because there is a document linked to it. But this truck doesn’t need a document (truck was copied by user) create a quick fix or a solution to this problem. |  |  |  | 17/12/2015 | 18/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0087 |  | Coil Number Hidden from the Ems system after wrong Mutation of order | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | The coil number 3086760 should be in the "Coil mgt- RM" after mutation process is end. But this case These coil number is disappear from the system. |  |  |  | 22/12/2015 | 22/12/2015 | 25/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0088 |  | Coil Numbers are missing in the shipments | Bug | High | Critical | Application support | V1.0 REL 01 | 8000 - Closed |  | Not Assigned |  | 102 Coil numbers are missing from the shipments program," mastercoil" tab. After mutation process these coils should be in the "masterccoil" tab with updated status. |  |  |  | 22/12/2015 | 05/01/2016 | 06/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0090 | Ticket_1278 | When printing Millsheet R663 it's not complete | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | When printing millsheet R663 The last lines are missing from the print. But when a pdf is generated in EMM it's complete. The missing lines are the signature of our director |  |  |  | 08/01/2016 | 22/01/2016 | 06/01/2016 | 24/02/2016 | 0 | 0 | 0
EMM6-0092 |  | Change status employee program from 100 to 900 | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Can you help to change the status of employees from 100- 900 . When we click update we must set the status to 900. It’s now not possible. |  |  |  | 12/01/2016 | 12/01/2016 | 06/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0093 |  | Error occurred while confirm task from "pio" program. | Bug | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | error message is poped up when user try to confirm the task from the "PIO" program. |  |  |  | 13/01/2016 | 21/01/2016 | 06/01/2016 | 25/01/2016 | 0 | 0 | 0
EMM6-0094 |  | Change the sequence of purchase order. | Feature Request | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Currently the sequence is: 2015001->2015652 But we need to change the sequence to 2016001 -> 2016652 So every new order will get the new sequence number. |  |  |  | 19/01/2016 | 20/01/2016 | 21/01/2016 | 21/01/2016 | 0 | 0 | 0
EMM6-0095 |  | Change the warning message to error message. | Task | Med | Moderate | Application support | V1.0 REL 01 | 8000 - Closed | Completed | Not Assigned |  | Change “EMM6-0068 Change Error message block into Warning Block” back to a Error block. This was a temporary request so now it can be changed back. |  |  |  | 19/01/2016 | 19/01/2016 | 21/01/2016 | 22/01/2016 | 0 | 0 | 0
EMM6-0097 |  | Program level security in PIO program | Change Request | Med | Minor |  | Unspecified | 8000 - Closed | Completed | Not Assigned |  | Trying to change and add the user group and users in the start security but cannot reflected in the System. |  |  |  | 10/02/2016 | 11/02/2016 | 21/01/2016 | 11/02/2016 | 0 | 0 | 0

## ReportModule
SR ID | Title | Type | Priority | Severity | Status | Assignee | Started | Resolved | Verified | Closed
EMM6-0083 | Laser Data Testing with Euro-Mit | Task | High | Major | 2000 - Open | hari
EMM6-0036 | Check Performance of the System to find performance related issues. | Task | Med | Moderate | 5000 - In Progress | amit | 01/10/2015
EMM6-0044 | CCC Task Management corrections | Change Request | High | Moderate | 5000 - In Progress | amit | 14/09/2015
EMM6-0055 | Customs quarter report | Change Request | Urg | Moderate | 5000 - In Progress | amit | 01/10/2015 | 02/11/2015
EMM6-0072 | Create a monthly report with SRM2FG and FG2SRM Updates | Task | Med | Moderate | 5000 - In Progress | neha | 29/12/2015 | 02/11/2015
EMM6-0074 | Enhance Laser Device Data Integration | Task | High | Major | 5000 - In Progress | amit | 19/11/2015 | 02/11/2015
EMM6-0077 | Wrong Cutting Number in Monthly Report | Bug | Med | Major | 5000 - In Progress | neha | 25/11/2015 | 02/11/2015
EMM6-0091 | Database Connection in EMM4 and convert to latest version | Task | Med | Moderate | 5000 - In Progress | amit | 11/01/2016 | 02/11/2015
EMM6-0096 | Problem with tab trucks in slit order | Bug | NP | Undefined | 5000 - In Progress | amit | 10/02/2016 | 02/11/2015
EMM6-0101 | Automation on the Shipments | Feature Request | Med | Moderate | 5000 - In Progress | amit | 16/02/2016 | 18/02/2016
EMM6-I-0015 | Deploying Euro-Mit Test System from Local Environment | Task | Med | Moderate | 5000 - In Progress | Not Assigned | 23/09/2015 | 18/02/2016
EMM6-I-0032 | Test every report for performance improvement | Task | Med | Major | 5000 - In Progress | neha | 24/02/2016 | 18/02/2016
EMM6-0004 | find solution for daily-customs-fix | Task | High | Major | 6000 - Resolved | hari | 15/07/2015 | 12/08/2015
EMM6-0008 | enhance R503 and R504 | Task | Low | Moderate | 6000 - Resolved | neha | 15/10/2015 | 24/02/2016
EMM6-0013 | change biz-logics regarding customs doc | Task | Med | Moderate | 6000 - Resolved | hari | 25/08/2015 | 24/02/2016
EMM6-0023 | Move sequence logic to trigger | Change Request | Med | Moderate | 6000 - Resolved | hari | 28/07/2015 | 12/08/2015
EMM6-0032 | Due date in iinvr749 | Bug | Med | Moderate | 6000 - Resolved | hari | 02/09/2015 | 02/09/2015
EMM6-0075 | Upgrade EMM5 System into Progress 11.5 Version | Task | Med | Major | 6000 - Resolved | frank | 25/01/2016 | 25/01/2016
EMM6-0078 | Modify CRM report in order to print 4 reports without using print/batch module | Task | Med | Minor | 6000 - Resolved | neha | 09/12/2015 | 24/02/2016
EMM6-0085 | Update Module so that sys and mo5 user group can set Cutting task status to 300 | Task | Med | Moderate | 6000 - Resolved | Not Assigned | 17/12/2015 | 23/12/2015
EMM6-0089 | Change the logic of import duties from 35.9 % to 0 according to the new Dutch rule. | Change Request | High | Major | 6000 - Resolved | amit | 08/01/2016 | 24/02/2016
EMM6-0098 | Change the field in companies to have 70 characters instead of 56 | Change Request | Med | Moderate | 6000 - Resolved | neha | 11/02/2016 | 24/02/2016
EMM6-0100 | No address in Client/Transporter, gives empty fields in CMR | Bug | Med | Moderate | 6000 - Resolved | neha | 16/02/2016 | 24/02/2016
EMM6-0102 | overwriting grade not working anymore | Bug | Med | Moderate | 6000 - Resolved | neha | 18/02/2016 | 24/02/2016
EMM6-0103 | Misplace of Coil number,purchase value in the shipment. | Bug | Med | Moderate | 6000 - Resolved | amit | 22/02/2016 | 24/02/2016
EMM6-0099 | Change purchvalue of mastercoil per coil | Change Request | Urg | Undefined | 7000 - Verified | marcovl | 11/02/2016 | 16/02/2016 | 24/02/2016
EMM6-0002 | Customs AD608 | Support SR | High | Major | 8000 - Closed | Not Assigned | 09/07/2015 | 17/11/2015 | 24/02/2016 | 30/11/2015
EMM6-0003 | convert R502 into xlsx | Feature Request | Low | Minor | 8000 - Closed | Not Assigned | 28/07/2015 | 29/07/2015 | 24/02/2016 | 09/02/2016
EMM6-0006 | text about customs must appear on salesinvoice | Task | High | Moderate | 8000 - Closed | Not Assigned | 10/07/2015 | 14/07/2015 | 04/02/2016 | 24/02/2016
EMM6-0007 | improve R569 | Task | Med | Moderate | 8000 - Closed | Not Assigned | 16/07/2015 | 10/08/2015 | 04/02/2016 | 24/02/2016
EMM6-0010 | validate mrn-nbr | Task | High | Moderate | 8000 - Closed | Not Assigned | 10/07/2015 | 14/07/2015 | 04/02/2016 | 11/02/2016
EMM6-0014 | hide widgets top-right-corner | Task | Low | Cosmetic | 8000 - Closed | Not Assigned | 15/07/2015 | 16/07/2015 | 04/02/2016 | 11/02/2016
EMM6-0018 | Create maintenance prograe to update temporary reference number to final reference number. | Task | Med | Moderate | 8000 - Closed | Not Assigned | 28/07/2015 | 29/07/2015 | 04/02/2016 | 11/02/2016
EMM6-0019 | Modify business logic so that users can input temporaray reference number. | Task | Low | Minor | 8000 - Closed | Not Assigned | 16/07/2015 | 16/07/2015 | 04/02/2016 | 11/02/2016
EMM6-0021 | remove block containing changed-by and such from every module in top-right-corner | Task | Med | Moderate | 8000 - Closed | Not Assigned | 06/07/2015 | 14/07/2015 | 04/02/2016 | 11/02/2016
EMM6-0022 | Laser Topic :- Make the API functionality working with progress | Task | High | Moderate | 8000 - Closed | Not Assigned | 26/06/2015 | 20/11/2015 | 04/02/2016 | 11/02/2016
EMM6-0025 | Import duties not on sales report | Bug | Med | Undefined | 8000 - Closed | Not Assigned | 21/08/2015 | 04/09/2015 | 25/01/2016 | 25/01/2016
EMM6-0026 | Force system to check IMA box in “trucks” | Change Request | Med | Undefined | 8000 - Closed | Not Assigned | 24/08/2015 | 15/09/2015 | 08/09/2015 | 11/02/2016
EMM6-0027 | Automatically calculating import duties | Bug | Med | Undefined | 8000 - Closed | Not Assigned | 24/08/2015 | 24/08/2015 | 08/09/2015 | 25/01/2016
EMM6-0028 | Not printing a line automatically on a invoice | Bug | Med | Undefined | 8000 - Closed | Not Assigned | 24/08/2015 | 01/09/2015 | 25/01/2016 | 24/02/2016
EMM6-0034 | Price in sizes | Change Request | Med | Moderate | 8000 - Closed | Not Assigned | 31/08/2015 | 04/09/2015 | 25/01/2016 | 11/02/2016
EMM6-0038 | Calculate import duties for NEU | Task | Med | Moderate | 8000 - Closed | Not Assigned | 10/09/2015 | 10/09/2015 | 25/01/2016 | 25/01/2016
EMM6-0039 | INF-1 report | Change Request | Med | Minor | 8000 - Closed | Not Assigned | 10/09/2015 | 11/09/2015 | 25/01/2016 | 11/02/2016
EMM6-0040 | Dollar bankaccount on invoice | Change Request | Med | Moderate | 8000 - Closed | Not Assigned | 10/09/2015 | 11/09/2015 | 25/01/2016 | 25/01/2016
EMM6-0043 | B8 value block does not work | Bug | High | Moderate | 8000 - Closed | Not Assigned | 15/09/2015 | 30/09/2015 | 03/11/2015 | 11/02/2016
EMM6-0048 | Can not set to Confirm staus once reset the value in some tasks | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 15/09/2015 | 23/12/2015 | 03/11/2015 | 11/02/2016
EMM6-0049 | Analyze for the empty i/iinvr520 report when user generate same report two times | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 18/09/2015 | 28/10/2015 | 25/01/2016 | 11/02/2016
EMM6-0050 | Change paperwork date in slit date | Change Request | Med | Moderate | 8000 - Closed | Not Assigned | 18/09/2015 | 21/09/2015 | 25/01/2016 | 24/02/2016
EMM6-0056 | Create necessary icons for laser device data integration | Feature Request | Med | Minor | 8000 - Closed | Not Assigned | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016
EMM6-0057 | when we insert our password in Emm5 live | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 08/10/2015 | 07/12/2015 | 25/01/2016 | 11/02/2016
EMM6-0058 | EMM Problem Import Duties | Bug | Urg | Critical | 8000 - Closed | Not Assigned | 08/10/2015 | 08/10/2015 | 25/01/2016 | 11/02/2016
EMM6-0059 | request small change layout invoice text | Change Request | Low | Cosmetic | 8000 - Closed | Not Assigned | 08/10/2015 | 05/01/2016 | 25/01/2016 | 24/02/2016
EMM6-0060 | Find Out Coil List and Status in which Bert has changed GradeName and in production till Date | Support SR | Urg | Critical | 8000 - Closed | Not Assigned | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016
EMM6-0061 | when coil number is ending with xj0 or higher it disappears | Bug | Med | Critical | 8000 - Closed | Not Assigned | 14/10/2015 | 09/11/2015 | 25/01/2016 | 25/01/2016
EMM6-0062 | Invoice Laminations shows no ADD duty on invoice | Bug | High | Major | 8000 - Closed | Not Assigned | 18/11/2015 | 18/11/2015 | 25/01/2016 | 11/02/2016
EMM6-0063 | revise the coilnumbersystem | Change Request | Med | Moderate | 8000 - Closed | Not Assigned | 30/10/2015 | 25/01/2016 | 25/01/2016 | 11/02/2016
EMM6-0064 | Check reports based on palletized or on produced materials for truck PW date and ETD date | Task | Med | Moderate | 8000 - Closed | Not Assigned | 28/10/2015 | 06/11/2015 | 25/01/2016 | 11/02/2016
EMM6-0065 | Create a report from the system with all NEU coils in Stock | Task | High | Major | 8000 - Closed | Not Assigned | 28/10/2015 | 04/11/2015 | 25/01/2016 | 24/02/2016
EMM6-0066 | Number of digits for "ADD.costs"box to small | Feature Request | Med | Cosmetic | 8000 - Closed | Not Assigned | 30/10/2015 | 18/11/2015 | 25/01/2016 | 24/02/2016
EMM6-0067 | Check if the value of CL/W1750+ and IndB8+ gets changed when Value of Grade has been changed. | Task | Med | Moderate | 8000 - Closed | Not Assigned | 30/10/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016
EMM6-0068 | Change Error message block into Warning Block | Task | Med | Moderate | 8000 - Closed | Not Assigned | 04/11/2015 | 04/11/2015 | 25/01/2016 | 25/01/2016
EMM6-0069 | Performance Issue in Capacity Checker Generating Report | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 06/11/2015 | 06/11/2015 | 25/01/2016 | 25/01/2016
EMM6-0070 | Analyze if the module is available to convert NEU coils into EU Coils | Task | High | Major | 8000 - Closed | Not Assigned | 17/11/2015 | 17/11/2015 | 25/01/2016 | 24/02/2016
EMM6-0071 | Develop a program module to convert NEU into EU and vice-versa | Task | High | Major | 8000 - Closed | Not Assigned | 17/11/2015 | 10/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0073 | Fix issue in Pallet Management for number out of Range | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 10/11/2015 | 18/11/2015 | 25/01/2016 | 25/01/2016
EMM6-0076 | Create a script which will list NEU FG coils | Task | Med | Moderate | 8000 - Closed | Not Assigned | 25/11/2015 | 26/11/2015 | 25/01/2016 | 25/01/2016
EMM6-0079 | Modify FileNo Field in order to accept 15 AlphaNumeric Value | Task | Med | Moderate | 8000 - Closed | Not Assigned | 08/12/2015 | 08/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0080 | Create Script to Delete some Trucks sent by Client | Task | Med | Minor | 8000 - Closed | Not Assigned | 09/12/2015 | 09/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0081 | Add Ref No. as per new coil numbering system with Slit Number | Task | Med | Moderate | 8000 - Closed | Not Assigned | 08/12/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016
EMM6-0082 | Change the Warning Messages according to New Numbering System | Change Request | Med | Moderate | 8000 - Closed | Not Assigned | 11/12/2015 | 20/01/2016 | 25/01/2016 | 24/02/2016
EMM6-0084 | Mutate a coil in Coil mgt – RM (o/ocoimrm.p) just like in Coil mgt – SRM. | Feature Request | High | Major | 8000 - Closed | Not Assigned | 17/12/2015 | 17/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0086 | Create a module to set a truck ex ems | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 17/12/2015 | 18/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0087 | Coil Number Hidden from the Ems system after wrong Mutation of order | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 22/12/2015 | 22/12/2015 | 25/01/2016 | 25/01/2016
EMM6-0088 | Coil Numbers are missing in the shipments | Bug | High | Critical | 8000 - Closed | Not Assigned | 22/12/2015 | 05/01/2016 | 06/01/2016 | 24/02/2016
EMM6-0090 | When printing Millsheet R663 it's not complete | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 08/01/2016 | 22/01/2016 | 06/01/2016 | 24/02/2016
EMM6-0092 | Change status employee program from 100 to 900 | Task | Med | Moderate | 8000 - Closed | Not Assigned | 12/01/2016 | 12/01/2016 | 06/01/2016 | 25/01/2016
EMM6-0093 | Error occurred while confirm task from "pio" program. | Bug | Med | Moderate | 8000 - Closed | Not Assigned | 13/01/2016 | 21/01/2016 | 06/01/2016 | 25/01/2016
EMM6-0094 | Change the sequence of purchase order. | Feature Request | Med | Moderate | 8000 - Closed | Not Assigned | 19/01/2016 | 20/01/2016 | 21/01/2016 | 21/01/2016
EMM6-0095 | Change the warning message to error message. | Task | Med | Moderate | 8000 - Closed | Not Assigned | 19/01/2016 | 19/01/2016 | 21/01/2016 | 22/01/2016
EMM6-0097 | Program level security in PIO program | Change Request | Med | Minor | 8000 - Closed | Not Assigned | 10/02/2016 | 11/02/2016 | 21/01/2016 | 11/02/2016

## Closed
S.No. | SR ID | Title | Type | Priority | Started | Resolved | Verified | Closed
1 | EMM6-0038 | Calculate import duties for NEU | Task | Med | 10/09/2015 | 10/09/2015 | 25/01/2016 | 25/01/2016 | Not needed
2 | EMM6-0039 | INF-1 report | Change Request | Med | 10/09/2015 | 11/09/2015 | 25/01/2016 | 11/02/2016 | Not needed
3 | EMM6-0040 | Dollar bankaccount on invoice | Change Request | Med | 10/09/2015 | 11/09/2015 | 25/01/2016 | 25/01/2016 | Not needed
4 | EMM6-0046 | Cash position split in USD and EURO | Change Request | Med | 15/09/2015 | 30/09/2015 | 03/11/2015 | 11/02/2016
5 | EMM6-0048 | Can not set to Confirm staus once reset the value in some tasks | Bug | Med | 15/09/2015 | 23/12/2015 | 03/11/2015 | 11/02/2016
6 | EMM6-0049 | Analyze for the empty i/iinvr520 report when user generate same report two times | Bug | Med | 18/09/2015 | 28/10/2015 | 25/01/2016 | 11/02/2016 | Not needed
7 | EMM6-0050 | Change paperwork date in slit date | Change Request | Med | 18/09/2015 | 21/09/2015 | 25/01/2016 | 24/02/2016 | Not needed
8 | EMM6-0056 | Create necessary icons for laser device data integration | Feature Request | Med | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016 | Not needed
9 | EMM6-0057 | when we insert our password in Emm5 live | Bug | Med | 08/10/2015 | 07/12/2015 | 25/01/2016 | 11/02/2016
10 | EMM6-0058 | EMM Problem Import Duties | Bug | Urg | 08/10/2015 | 08/10/2015 | 25/01/2016 | 11/02/2016 | Not needed
11 | EMM6-0059 | request small change layout invoice text | Change Request | Low | 08/10/2015 | 05/01/2016 | 25/01/2016 | 24/02/2016
12 | EMM6-0060 | Find Out Coil List and Status in which Bert has changed GradeName and in production till Date | Task | Urg | 15/10/2015 | 15/10/2015 | 25/01/2016 | 25/01/2016 | Not needed
13 | EMM6-0061 | when coil number is ending with xj0 or higher it disappears | Bug | Med | 14/10/2015 | 09/11/2015 | 25/01/2016 | 25/01/2016 | Not needed
14 | EMM6-0062 | Invoice Laminations shows no ADD duty on invoice | Bug | High | 18/11/2015 | 18/11/2015 | 25/01/2016 | 11/02/2016 | Not needed
15 | EMM6-0063 | revise the coilnumbersystem | Change Request | Med | 30/10/2015 | 25/01/2016 | 25/01/2016 | 11/02/2016
16 | EMM6-0064 | Check reports based on palletized or on produced materials for truck PW date and ETD date | Task | Med | 28/10/2015 | 06/11/2015 | 25/01/2016 | 11/02/2016 | Not needed
17 | EMM6-0065 | Create a report from the system with all NEU coils in Stock | Task | High | 28/10/2015 | 04/11/2015 | 25/01/2016 | 24/02/2016 | Not needed
18 | EMM6-0066 | Number of digits for "ADD.costs"box to small | Feature Request | Med | 30/10/2015 | 18/11/2015 | 25/01/2016 | 24/02/2016 | Not needed
19 | EMM6-0067 | Check if the value of CL/W1750+ and IndB8+ gets changed when Value of Grade has been changed. | Task | Med | 30/10/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016 | Not needed
20 | EMM6-0068 | Change Error message block into Warning Block | Task | Med | 04/11/2015 | 2015-04-11 | 25/01/2016 | 25/01/2016 | Not needed
21 | EMM6-0069 | Performance Issue in Capacity Checker Generating Report | Bug | Med | 06/11/2015 | 06/11/2015 | 25/01/2016 | 25/01/2016 | Not needed
22 | EMM6-0070 | Analyze if the module is available to convert NEU coils into EU Coils | Task | High | 17/11/2015 | 17/11/2015 | 25/01/2016 | 24/02/2016 | Not needed
23 | EMM6-0071 | Develop a program module to convert NEU into EU and vice-versa | Task | High | 17/11/2015 | 10/12/2015 | 25/01/2016 | 25/01/2016 | Not needed
24 | EMM6-0073 | Fix issue in Pallet Management for number out of Range | Bug | Med | 10/11/2015 | 18/11/2015 | 25/01/2016 | 25/01/2016 | Not needed
25 | EMM6-0076 | Create a script which will list NEU FG coils | Task | Med | 25/11/2015 | 26/11/2015 | 25/01/2016 | 25/01/2016 | Not needed
26 | EMM6-0079 | Modify FileNo Field in order to accept 15 AlphaNumeric Value | Task | Med | 08/12/2015 | 08/12/2015 | 25/01/2016 | 25/01/2016
27 | EMM6-0080 | Create Script to Delete some Trucks sent by Client | Task | Med | 09/12/2015 | 09/12/2015 | 25/01/2016 | 25/01/2016
28 | EMM6-0081 | Add Ref No. as per new coil numbering system with Slit Number | Task | Med | 08/12/2015 | 25/01/2016 | 25/01/2016 | 24/02/2016
29 | EMM6-0082 | Change the Warning Messages according to New Numbering System | Change Request | Med | 11/12/2015 | 20/01/2016 | 25/01/2016 | 24/02/2016
30 | EMM6-0084 | Mutate a coil in Coil mgt – RM (o/ocoimrm.p) just like in Coil mgt – SRM. | Feature Request | High | 17/12/2015 | 17/12/2015 | 25/01/2016 | 25/01/2016
31 | EMM6-0086 | Create a module to set a truck ex ems | Bug | Med | 17/12/2015 | 18/12/2015 | 25/01/2016 | 25/01/2016
32 | EMM6-0087 | Coil Number Hidden from the Ems system after wrong Mutation of order | Bug | Med | 22/12/2015 | 22/12/2015 | 25/01/2016 | 25/01/2016
33 | EMM6-0088 | Coil Numbers are missing in the shipments | Bug | High | 22/12/2015 | 05/01/2016 | 06/01/2016 | 24/02/2016
34 | EMM6-0090 | When printing Millsheet R663 it's not complete | Bug | Med | 08/01/2016 | 22/01/2016 | 06/01/2016 | 24/02/2016
35 | EMM6-0092 | Change status employee program from 100 to 900 | Task | Med | 12/01/2016 | 12/01/2016 | 06/01/2016 | 25/01/2016
36 | EMM6-0093 | Error occurred while confirm task from "pio" program. | Bug | Med | 13/01/2016 | 21/01/2016 | 06/01/2016 | 25/01/2016
37 | EMM6-0094 | Change the sequence of purchase order. | Feature Request | Med | 19/01/2016 | 20/01/2016 | 21/01/2016 | 21/01/2016
38 | EMM6-0095 | Change the warning message to error message. | Task | Med | 19/01/2016 | 19/01/2016 | 21/01/2016 | 22/01/2016
39 | EMM6-0097 | Program level security in PIO program | Change Request | Med | 10/02/2016 | 11/02/2016 | 21/01/2016 | 11/02/2016
40 | EMM6-0099 | Change purchvalue of mastercoil per coil | Change Request | Urg | 11/02/2016 | 16/02/2016 | 24/02/2016
|  |  |  | SR Type | Urgent Priority | High Priority | Medium Priority | Low Priority | Total
|  |  |  | Bug | 1 | 3 | 13 |  | 17
|  |  |  | Task | 1 | 5 | 13 | 2 | 21
|  |  |  | Change Request | 1 |  | 8 | 1 | 10
|  |  |  | Feature Request |  | 1 | 3 | 1 | 5

## Resolved
S.No. | SR ID | Title | Type | Priority | Started | Resolved
1 | EMM6-0008 | enhance R503 and R504 | Task | Low | 15/10/2015 | 24/02/2016
2 | EMM6-0013 | change biz-logics regarding customs doc | Task | Med | 25/08/2015 | 24/02/2016
3 | EMM6-0075 | Upgrade EMM5 System into Progress 11.5 Version | Task | Med | 25/01/2016 | 25/01/2016 | not needed
4 | EMM6-0078 | Modify CRM report in order to print 4 reports without using print/batch module | Task | Med | 09/12/2015 | 24/02/2016
5 | EMM6-0085 | Update Module so that sys and mo5 user group can set Cutting task status to 300 | Task | Med | 17/12/2015 | 23/12/2015
6 | EMM6-0089 | Change the logic of import duties from 35.9 % to 0 according to the new Dutch rule. | Change Request | High | 08/01/2016 | 24/02/2016
7 | EMM6-0098 | Change the field in companies to have 70 characters instead of 56 | Change Request | Med | 11/02/2016 | 24/02/2016
8 | EMM6-0100 | No address in Client/Transporter, gives empty fields in CMR | Bug | Med | 16/02/2016 | 24/02/2016
9 | EMM6-0102 | overwriting grade not working anymore | Bug | Med | 18/02/2016 | 24/02/2016
10 | EMM6-0103 | Misplace of Coil number,purchase value in the shipment. | Bug | Med | 22/02/2016 | 24/02/2016
[8 empty] | SR Type | High Priority | Medium Priority | Low Priority | Total
[8 empty] | Bug |  | 4 |  | 4
[8 empty] | Task | 1 | 1 | 4 | 6
[8 empty] | Change Request | 1 | 1 | 1 | 3

## InProgress
S.No. | SR ID | Title | Type | Priority | Started
1 | EMM6-0036 | Check Performance of the System to find performance related issues. | Task | Med | 01/10/2015
2 | EMM6-0044 | CCC Task Management corrections | Change Request | High | 14/09/2015
3 | EMM6-0055 | Customs quarter report | Change Request | Urg | 01/10/2015
4 | EMM6-0072 | Create a monthly report with SRM2FG and FG2SRM Updates | Task | Med | 29/12/2015
5 | EMM6-0074 | Enhance Laser Device Data Integration | Task | High | 19/11/2015
6 | EMM6-0077 | Wrong Cutting Number in Monthly Report | Bug | Med | 25/11/2015
7 | EMM6-0091 | Database Connection in EMM4 and convert to latest version | Task | Med | 11/01/2016
8 | EMM6-0096 | Problem with tab trucks in slit order | Bug | Med | 10/02/2016
9 | EMM6-0101 | Automation on the Shipments | Feature Request | Med | 16/02/2016
10 | EMM6-I-0015 | Deploying Euro-Mit Test System from Local Environment | Task | Med | 23/09/2015
11 | EMM6-I-0032 | Test every report for performance improvement | Task | Med | 24/02/2016
[6 empty] | SR Type | Urgent Priority | High Priority | Medium Priority | Total
[6 empty] | Bug |  |  | 2 | 2
[6 empty] | Task |  | 1 | 5 | 6
[6 empty] | Change Request | 1 | 1 |  | 2
[6 empty] | Feature Request |  |  | 1 | 1